Task 3A — Weekly Status Update (3 Accounts)

To: Team Lead   |   From: AI Business Analyst   |   Re: Week 4 — FreshBasket, UrbanPulse, NestWell

The numbers

- FreshBasket (Organic Snacks): ₹2.5L spend, ROAS 4.2 — on track. 9 hrs. Client content.

- UrbanPulse (Men's Grooming): ₹4L spend, ROAS 2.1 vs 3.0 target — Month 2, algo still learning. 12 hrs. Client questioning results.

- NestWell (Home Fragrances): ₹1.8L spend, ROAS 3.5 — on target. 7 hrs. Routine.

What connects across the three (the part that isn't in the numbers)

- Report design is the real issue, not a one-off question. FreshBasket (Tue) and NestWell (Wed) independently asked the exact same thing — "what does the daily spend breakdown mean, the columns are confusing." Two of three clients can't read our standard report. That's not three support tickets; it's one design defect. Fix: redesign the report column layout / add a one-line legend, and ship it to all accounts, not just the two who asked.

- UrbanPulse's risk is perception, not performance. It consumed 12 hrs this week — ~33% more than FreshBasket — on keyword restructuring, negative-keyword audit and competitive analysis, yet the client feels "nothing is happening" and is anchoring on a previous agency's Month-1 ROAS. The effort is invisible. If we don't translate those 12 hours into something the client can see, this account churns around Month 3 regardless of where ROAS lands. Fix: a short 'work done + why ROAS lags early' note, and reset the Month-1-vs-learning-phase expectation explicitly.

- UrbanPulse ROAS may be partly a listing problem, not an ads problem. Their product images are weaker than category competitors. We can optimise bids all day; if the click lands on a weaker page, conversion caps our ROAS. Worth flagging to the client's creative side.

- NestWell has an un-worked channel sitting in plain sight. Their Flipkart store is live but unadvertised and they haven't asked about it. That's a cross-sell signal, not just a note — worth raising as a test.

One thing I'd change about how we work

Make effort visible by default. UrbanPulse shows that hours spent ≠ trust earned unless we narrate the work. A lightweight 'what we did and why' line on every report would prevent the silent-churn pattern and would also have surfaced the report-confusion issue sooner.

Task 3B — MD Talking Points: UrbanPulse

Chosen account: UrbanPulse (Men's Grooming). 15-min call with the MD on next-quarter Amazon growth. Lens shifts from KPIs to topline, margin, competitive position and new channels — no ROAS/ACOS language.

Where you stand & where it's heading

- Amazon is in its build phase — we're investing now to compound revenue and margin later, not chasing a one-month number. The channel is being set up to carry itself.

- Frame the trajectory in revenue terms, not campaign terms: the goal this quarter is moving from ad-dependent sales toward a growing organic base, which is what makes the channel more profitable over time.

Growth ideas I'd bring

- Listing quality is a topline lever, not a design detail. Competitors' product pages convert better than ours. Upgraded images/content lifts conversion on every rupee already being spent — the cheapest revenue gain available, and it compounds into organic rank.

- Shift from harvesting demand to creating it. Move beyond defending existing searches toward formats that win new-to-brand customers, expanding share in the men's grooming subcategory rather than just maintaining position.

- Second channel test. If UrbanPulse has (or could open) Flipkart, a small ring-fenced test validates a second revenue stream where competition for keywords is lighter. Framed as: 'where does the next increment of revenue come from once Amazon matures?'

Questions I'd ask the MD

- For next quarter, are you prioritising topline growth (invest, enter channels) or margin (hold spend, let organic carry more)? That single answer reshapes the 90-day plan.

- Where does Amazon sit in your overall growth plan vs D2C / retail / other marketplaces?

- Is there appetite to test a second e-commerce channel this quarter, and what revenue would make that test 'worth it' to you?

What I'd want that I don't have yet

- Total Amazon revenue and organic-vs-paid split (I see campaign ROAS, not the full topline or margin-after-fees).

- Gross margin after COGS + Amazon fees + our retainer, to talk bottomline credibly.

- Category size/growth and where UrbanPulse ranks in its subcategory, and the company's annual revenue target — so growth ideas are sized to the MD's actual ambition.